SCALE ARMY

Pod & Role-Level Retention Dashboard

Project Implementation Plan

Version 2.0 — includes Markdown Skills framework & build order

Prepared by: HR Manager  •  May 2026

# 1. Project Overview

This plan covers the implementation of Dashboard 2 — the Pod & Role-Level Retention Dashboard — for Scale Army's HR function. Version 2.0 adds a Markdown Skills framework and a clear build order so that every future data refresh or dashboard update follows the same consistent process without having to rediscover how things were built.

Problem: Scale Army's talent data shows a 59% overall loss rate across 780 placements, with 69% of exits occurring within the first 3 months. Without a centralized view by pod, role, and recruiter, the HR team cannot prioritize retention efforts or act on the data systematically.

Solution: A production-grade interactive React dashboard with three tabs: Pod Overview, Role Breakdown, and Recruiter Analysis. Backed by a set of reusable Markdown skill files that ensure future data refreshes, new dashboards, and analysis requests all follow the same methodology.

# 2. Objectives

- Provide HR with a real-time, filterable view of attrition by pod, role, and recruiter

- Identify structural retention risks distinguishable from individual performance issues

- Enable evidence-based conversations with team leads and account managers

- Establish a baseline for tracking improvement over time

- Build a library of reusable Markdown skills so future data work is consistent and repeatable

- Reduce monthly HR reporting time from 3–4 hours to under 30 minutes

# 3. Scope

## 3.1 In Scope

- Interactive React dashboard — Pod Overview, Role Breakdown, Recruiter Analysis tabs

- Integration with All Sales sheet as primary data source

- Three Markdown skill files: data-refresh, dashboard-update, hr-analysis (detailed in Section 5)

- Deployment to internal HR tooling (Claude.ai or equivalent)

- User guide and skill usage documentation

## 3.2 Out of Scope

- Real-time data pipeline (Phase 1 uses static data; live sync is future roadmap)

- Individual talent profile pages or PII-level data exposure

- Client-facing reporting views (Dashboard 3)

- Mobile layout optimization

- Automated alert or notification systems

# 4. What Is a Markdown Skill?

A Markdown skill is a plain-text instruction file (saved as SKILL.md) that tells Claude exactly how to handle a specific, repeatable task. Think of it as a recipe card: once it exists, anyone on the HR team can hand Claude new data and get a consistent, high-quality result without re-explaining the process each time.

Each skill file has three parts:

- A header block (YAML frontmatter) that names the skill and describes when to use it

- Step-by-step instructions for how Claude should approach the task

- Optional reference files — for example, the column definitions from the All Sales sheet

Skills live in a shared folder accessible to Claude. When you drop in a new weekly Excel file and say 'run the data refresh', Claude reads the relevant skill and follows its instructions precisely — same method every week, regardless of who is asking.

Why this matters for weekly data Every week Scale Army receives new placement data. Without a skill file, each refresh risks: different column mappings, inconsistent metric calculations, charts that break when a new role or pod appears. With skill files in place, the refresh is a single prompt — Claude reads the skill, processes the new data, validates it, and updates the dashboard following the exact same steps as last week.

# 5. Markdown Skills to Build

Three skill files will be created as part of this project. They are designed to work together: the data-refresh skill feeds clean data to the dashboard-update skill, and the hr-analysis skill draws on both to produce narrative insights.

Skill 1 scale-army-data-refresh

File: skills/scale-army-data-refresh/SKILL.md Purpose: Process a new weekly Scale Army Excel file into a clean, validated JSON dataset ready for the dashboard. Triggers when: HR Manager says 'new data arrived', 'update with this week's file', or uploads an xlsx to Claude. Contents: - Step-by-step instructions for reading the All Sales sheet (column names, data types, date format handling) - Validation rules — flag missing start/end dates, unknown pod names, null talent names - Transformation logic — how to calculate loss rate, tenure buckets (0–3mo, 3–6mo, 6–12mo, 12mo+), and avg tenure - Output format spec — the exact JSON structure the dashboard expects - Edge case handling — Cold Caller / Bulk Hiring outlier flag, EOR status normalization - Reference file: column_definitions.md listing every field in the All Sales sheet

Skill 2 scale-army-dashboard-update

File: skills/scale-army-dashboard-update/SKILL.md Purpose: Update Dashboard 2 (the React artifact) with fresh data produced by the data-refresh skill. Triggers when: HR Manager says 'update the dashboard', 'refresh the charts', or provides a new JSON data file. Contents: - Instructions for swapping the data constants in the React component (PODS, ROLES, RECRUITERS arrays) - How to handle new pods or roles that did not exist in the prior dataset (add card, do not silently drop) - Outlier detection rule — if any role has loss rate > 85%, add the callout banner automatically - Color-coding logic — which loss-rate thresholds map to red / orange / yellow / green - Checklist of visual elements to verify after each update (all four pod cards render, tenure pie sums to 100%, recruiter table sorted correctly) - Version-bump instruction — update the subtitle date on each refresh

Skill 3 scale-army-hr-analysis

File: skills/scale-army-hr-analysis/SKILL.md Purpose: Generate a structured HR narrative from the latest dataset — suitable for monthly reports or stakeholder briefings. Triggers when: HR Manager says 'write the monthly analysis', 'summarize this week's retention data', or 'prepare the report for leadership'. Contents: - Template structure: Executive Summary (3 sentences), Pod Highlights, Roles to Watch, Recruiter Context, Recommended Actions - Which metrics to always include: overall loss rate vs. prior period, pod with biggest change, top exit role, avg tenure trend - Tone guidance: systemic framing — issues are structural, not individual performance criticisms - Contextualisation rule — always note if Cold Caller / Bulk Hiring is included or excluded from overall figures - Output format: Word document using the existing project plan formatting conventions - Reference file: insight_examples.md with sample phrasings for common patterns (e.g. early churn spike, buyout rate increase)

How the three skills connect in a weekly refresh 1. HR Manager uploads new Excel file and says 'process this week's data' 2. Claude reads scale-army-data-refresh → validates and transforms → outputs clean JSON 3. Claude reads scale-army-dashboard-update → updates React constants → verifies visuals 4. Claude reads scale-army-hr-analysis → generates Word report → HR Manager reviews and shares Total HR time for a weekly refresh once skills are live: ~15 minutes.

# 6. Build Order

The steps below define the exact sequence for building the project. Steps marked with a teal background produce a Markdown skill file as their primary output. Every other step produces dashboard, data, or documentation artifacts. Each step depends on the one before it — do not skip ahead.

| 1 | Stakeholder alignment & requirements sign-off Confirm KPIs, filters, pod definitions, and audience with HR leadership. Lock scope before any building begins. Outputs: Signed requirements brief, approved filter list |
| --- | --- |

| 2 | Data audit — All Sales sheet Inspect the uploaded xlsx for null rates, date formats, pod naming consistency, and edge cases (EOR status, Cold Caller outlier). Document every column, its type, and its known quirks. Outputs: column_definitions.md — the reference file used by Skill 1 |
| --- | --- |

| 3 | Write Skill 1: scale-army-data-refresh ← Creates Skill 1 Author the SKILL.md using findings from the data audit. Define validation rules, transformation logic, and the output JSON schema. Test by running Claude against the mock dataset and comparing output to hand-calculated figures. Outputs: skills/scale-army-data-refresh/SKILL.md + column_definitions.md |
| --- | --- |

| 4 | Build dashboard data layer Using Skill 1, transform the mock dataset into the JSON constants (PODS, ROLES, RECRUITERS). This is the first live use of the skill — treat it as a real-world test of Skill 1's instructions. Outputs: Validated JSON data file, any Skill 1 corrections logged |
| --- | --- |

| 5 | Build & style the React dashboard Implement all three tabs (Pod Overview, Role Breakdown, Recruiter Analysis) using the validated JSON from Step 4. Apply the Scale Army color system and branded typography. Outputs: Working React dashboard artifact |
| --- | --- |

| 6 | Write Skill 2: scale-army-dashboard-update ← Creates Skill 2 Document the exact process for updating the dashboard with new data: which arrays to swap, how to handle new roles/pods, outlier detection rules, and the post-update verification checklist. Outputs: skills/scale-army-dashboard-update/SKILL.md |
| --- | --- |

| 7 | Data integration — connect to live source Map the dashboard data model to the live Scale Army pipeline. Build the transformation script. Test a full cycle: new xlsx in → Skill 1 → JSON → Skill 2 → updated dashboard. Outputs: Transformation script, end-to-end refresh test report |
| --- | --- |

| 8 | Write Skill 3: scale-army-hr-analysis ← Creates Skill 3 Define the report template, required metrics, tone guidelines, and contextualisation rules. Include insight_examples.md with sample phrasings. Test by generating a monthly report from the mock data. Outputs: skills/scale-army-hr-analysis/SKILL.md + insight_examples.md |
| --- | --- |

| 9 | Testing & QA Run a complete end-to-end refresh using all three skills. Cross-browser test the dashboard. Validate 20 records against source data. Conduct user acceptance testing with 2–3 HR team members. Outputs: Browser QA report, accuracy sign-off, UAT sign-off |
| --- | --- |

| 10 | Deployment & handover Deploy dashboard to production. Host skill files in the shared Claude workspace. Deliver user guide explaining how to trigger each skill. Run a walkthrough session with stakeholders. Outputs: Live dashboard URL, skill files installed, user guide, maintenance runbook |
| --- | --- |

## Build Order at a Glance

| Step | Activity | Timing | Primary Output |
| --- | --- | --- | --- |
| Step 1 | Stakeholder alignment | Week 1 | Requirements brief |
| Step 2 | Data audit | Week 1 | column_definitions.md |
| Step 3 | Skill 1: data-refresh | Week 2 | SKILL.md + reference file |
| Step 4 | Dashboard data layer | Week 2 | Validated JSON |
| Step 5 | React dashboard build | Week 3 | Working artifact |
| Step 6 | Skill 2: dashboard-update | Week 3 | SKILL.md |
| Step 7 | Live data integration | Week 4 | Transformation script |
| Step 8 | Skill 3: hr-analysis | Week 4–5 | SKILL.md + insight examples |
| Step 9 | Testing & QA | Week 5 | QA & UAT sign-offs |
| Step 10 | Deployment & handover | Week 6 | Live URL + all skills installed |

# 7. Project Phases & Timeline

Total estimated duration: 6 weeks. All timelines assume part-time HR involvement (3–4 hours/week) and a dedicated developer resource (50% allocation). Skill-writing tasks are owned jointly by the HR Manager (who defines the business rules) and the developer (who tests and refines).

## Phase 1 — Discovery & Requirements (Week 1)

| Phase | Task | Duration | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| Ph. 1 | Stakeholder alignment — confirm KPIs, filters, audience (Build Order Step 1) | 2 days | HR Manager | Signed requirements brief |
| Ph. 1 | Data audit of All Sales sheet — document columns, types, nulls, edge cases (Step 2) | 2 days | HR Manager + Dev | column_definitions.md |
| Ph. 1 | Review and approve existing Dashboard 2 prototype | 1 day | HR Manager | Design sign-off |

## Phase 2 — Skills & Development (Week 2–4)

| Phase | Task | Duration | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| Ph. 2 | Author Skill 1: scale-army-data-refresh (Step 3) | 2 days | HR Manager + Dev | SKILL.md v1 |
| Ph. 2 | Test Skill 1 against mock data; refine rules and output schema (Step 4) | 2 days | HR Manager + Dev | Validated JSON + Skill 1 v2 |
| Ph. 2 | Build Pod Overview tab with interactive tenure drill-down (Step 5) | 3 days | Developer | Working pod tab |
| Ph. 2 | Build Role Breakdown and Recruiter Analysis tabs (Step 5) | 2 days | Developer | Working role + recruiter tabs |
| Ph. 2 | Implement filters (pod, date range) across all tabs (Step 5) | 2 days | Developer | Filtered dashboard |
| Ph. 2 | Author Skill 2: scale-army-dashboard-update (Step 6) | 1 day | HR Manager + Dev | SKILL.md v1 |
| Ph. 2 | Internal HR review and feedback round | 2 days | HR Manager | Feedback log |

## Phase 3 — Data Integration & Skill 3 (Week 4–5)

| Phase | Task | Duration | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| Ph. 3 | Map dashboard data model to live data source (Step 7) | 2 days | Developer + IT | Data mapping doc |
| Ph. 3 | Build transformation script; run end-to-end refresh test (Step 7) | 3 days | Developer | Transformation script + test report |
| Ph. 3 | Author Skill 3: scale-army-hr-analysis (Step 8) | 2 days | HR Manager + Dev | SKILL.md + insight_examples.md |
| Ph. 3 | Test Skill 3 — generate monthly report from mock data; refine template (Step 8) | 1 day | HR Manager | Sample report + Skill 3 v2 |
| Ph. 3 | Set up weekly data refresh schedule | 1 day | IT / Developer | Refresh schedule |

## Phase 4 — Testing & QA (Week 5)

| Phase | Task | Duration | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| Ph. 4 | Full end-to-end test: xlsx → Skill 1 → Skill 2 → dashboard (Step 9) | 1 day | HR Manager + Dev | End-to-end test report |
| Ph. 4 | Data accuracy validation — spot-check 20 records | 1 day | HR Manager | Accuracy sign-off |
| Ph. 4 | Cross-browser testing (Chrome, Edge, Safari) | 1 day | Developer | Browser QA report |
| Ph. 4 | User acceptance testing with 2–3 HR team members | 2 days | HR Manager | UAT sign-off |

## Phase 5 — Deployment & Handover (Week 6)

| Phase | Task | Duration | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| Ph. 5 | Deploy dashboard to production; install skill files in shared workspace (Step 10) | 1 day | Developer + IT | Live dashboard URL + skills installed |
| Ph. 5 | Create HR user guide — how to trigger each skill, what to check after each run | 2 days | HR Manager + Dev | User guide document |
| Ph. 5 | Walkthrough session with HR and management stakeholders | Half day | HR Manager | Session notes |
| Ph. 5 | Document maintenance runbook — data refresh ownership, skill update process | 1 day | Developer | Maintenance runbook |
| Ph. 5 | Project close-out and lessons learned | Half day | HR Manager | Lessons learned log |

# 8. Stakeholders & Responsibilities

| Role | Responsibility | Involvement | Success Metric |
| --- | --- | --- | --- |
| HR Manager | Project owner; defines business rules for all three skills | Daily — requirements, skill authoring, UAT | Dashboard live; all 3 skills installed and tested |
| Developer / Engineer | Build dashboard; co-author and test skill files | Full-time Phases 2–5 | All tabs functional; skills produce correct outputs |
| IT / Infrastructure | Hosting, access, weekly data pipeline | Part-time Phases 3 & 5 | Secure deployment; refresh schedule active |
| Team Pod Leads | Validate pod-level data accuracy and column definitions | Phase 1 data audit + Phase 3 review | Definitions confirmed; no disputed records |
| HR Leadership | Strategic alignment; end-user of hr-analysis skill output | Phase 1 kick-off + Phase 5 demo | Approved for ongoing use; reports adopted in monthly cycle |

# 9. Success Metrics

| Metric | Baseline | Target | Measurement |
| --- | --- | --- | --- |
| Overall loss rate | 59% across all pods | < 50% within 12 months | Monthly dashboard review |
| Pod 4 loss rate | 93.4% (Bulk Hiring) | < 80% within 6 months | Pod Overview tab |
| Early churn (0–3 months) | 69% of exits in first 3 months | < 55% within 3 months | Tenure bucket chart |
| Cold Caller exits | 142 exits, 93.4% loss rate | 25% reduction YoY | Role Breakdown tab |
| HR reporting time | ~3–4 hrs/month (manual) | < 30 min/month (skill-assisted) | Self-reported by HR team |
| Skill reliability | N/A (new) | Zero manual corrections needed in 4 consecutive refreshes | Refresh log |

# 10. Risks & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Data quality issues in source xlsx (nulls, date format changes, renamed columns) | High | High | Skill 1 includes explicit null-handling and column-name aliases; data audit in Phase 1 catches known issues before skills are written |
| Skill files become outdated as data structure evolves | Medium | High | Skill files stored in version-controlled folder; any schema change triggers a skill update task in the maintenance runbook |
| Recruiter / pod lead pushback on attrition visibility | Medium | Medium | Frame as systemic insight tool; include role-mix contextualisation note in Skill 3 report template |
| Cold Caller outlier skewing overall metrics | High | Low | Skill 2 includes automatic outlier flag; Skill 3 always notes whether Bulk Hiring is included or excluded from figures |
| Developer unavailability causing delays | Low | High | Prototype already exists; Skill 1 and Skill 3 can be drafted by HR Manager without developer involvement |
| Data refresh cadence not maintained after go-live | High | Medium | Maintenance runbook assigns named owner and sets calendar reminders; Skill 1 designed to be runnable by HR Manager without technical help |
| Scope creep into client-level or talent-level views | Medium | Medium | Scope boundary documented in requirements brief; deferred items logged in a Dashboard 3 backlog |

# 11. Assumptions & Dependencies

## Assumptions

- The All Sales sheet is the agreed-upon source of truth for placement data

- HR Manager can commit 3–4 hours per week across all phases

- A React-experienced developer is available at 50% allocation for Phases 2–5

- Skill files will be hosted in a shared Claude workspace accessible to the HR Manager

- Phase 1 launches with static data; live data integration is Phase 3 (not pre-launch)

- Stakeholders accept that skill files will require minor updates as data evolves — this is normal maintenance, not rework

## Dependencies

- Access to the live Scale Army data pipeline (Phase 3 integration)

- IT sign-off on hosting environment and skill file storage location

- Pod lead availability for the column definition review session (Phase 1)

- HR leadership availability for kick-off (Week 1) and demo (Week 6)

# 12. Immediate Next Steps

Complete these five actions within the next 5 business days to kick off the project:

1.  Schedule stakeholder alignment meeting (HR Manager + HR Leadership)

2.  Confirm developer resource and agree on start date

3.  Begin data audit — open the All Sales sheet and start drafting column_definitions.md

4.  Confirm skill file hosting location with IT (shared Claude workspace or folder)

5.  Share Dashboard 2 prototype with stakeholders for early feedback before Week 2 build begins

Scale Army  •  Dashboard 2 Project Plan v2.0  •  May 2026